## Status Report
Futionality | Test Cases | Executed | Passed | Failed | Blocked / Pending | Descpoed | Comments / Risks | Tester(s) | Status | Results
Authorization API | 31 | 27 | 19 | 4 | 1 | 4 |  | KB MGAZI | Execution % Complete | 92%
Dispute API | 36 | 32 | 31 | 1 | 0 | 4 | optional | KB MGAZI | Pass % | 88%
Refund API | 11 | 11 | 10 | 1 | 0 | 0 | I need A/c no. for WIP | KB MGAZI | Fail % | 8%
Verification API | 11 | 11 | 11 | 0 | 0 | 0 |  | KB MGAZI | Blocked % | 1%
Customer API | 7 | 7 | 6 | 1 | 0 | 0 | Why am I unable to update email address for Customer Update API | KB MGAZI | Start Date | 18/11/2025
DVA APPI | 9 | 9 | 8 | 1 |  |  |  | KB MGAZI | End Date (Planned) | 21/11/2025
Total Test Cases | 105 | 97 | 85 | 8 | 1 | 8 |  |  | End Date (Actual) | 21/11/2026
[9 empty] | Comments / Risks | Pending Defects
Formula: =Executed/Total Test Cases*100
Formula: =Passed/Executed*100
Formula: =Failed/Executed*100
Formula: =Blocked/Executed*100

## AUTHORIZATION API
Test Case ID | API / Feature | Title | Description | Pre-conditions | Steps | Test Data | Expected Result | Status
TC-AUTH-001 | POST /transaction/initialize | Initialize Transaction | Successful initialization with valid amount + email | API Keys configured (test mode) Valid email & amount Card: 5425233430109903 – Success (00) | 1. Send POST /transaction/initialize 2. Include amount, email, callback_url 3.Redirect to Paystack payment page | Use success test card to complete payment ¦ Amount = 500 Email = test@example.com Callback URL = https://callback.test Card: 5425233430109903 CVV: 123 Expiry: 12/27 | 200 OK with reference | Pass
TC-AUTH-002 | POST /transaction/initialize | Initialize Transaction | Validate that the Paystack-proxy API successfully initializes a high-value card transaction and returns the correct authorization URL or appropriate ISO-mapped error response. | • Merchant is active and has valid Paystack secret key • Paystack proxy route is configured and reachable • Card meets 3-D Secure requirements (if applicable) • Amount exceeds high-value threshold (e.g., > ZAR 5,000) | 1. Send POST request to /transaction/initialize with high-value amount 2. Include required fields: email, amount, currency, metadata 3. Observe API response 4. Validate returned status, reference, and authorization URL 5. Verify response mapping to ISO 8583 code (if failure) | email: testuser@example.com • amount: 750000 (ZAR 7,500.00) • currency: ZAR or NGN depending on environment • callback_url: https://example.com/success • metadata: { "order_id": "ORD-99881", "channel": "web" } | Processed normally | Pass
TC-AUTH-003 | POST /transaction/initialize | Initialize Transaction | Validate that the API returns an appropriate error when the amount field is omitted from the request body. | • Merchant account is active • Request body is valid except for the missing amount field | 1. Send POST request to /transaction/initialize. 2. Exclude the amount field from the JSON body. 3. Submit the request. 4. Observe validation error in response. | Request Body: { "email": "test@example.com " } | 400: “Amount is required | Pass
TC-AUTH-004 | POST /transaction/initialize | Initialize Transaction | Validate that the API rejects a request where amount = 0. | • Merchant account is active • Request body is valid except amount = 0 | 1. Send POST request to /transaction/initialize. 2. Set amount to 0. 3. Submit the request. 4. Observe validation error in response. | Request Body: { "email": "test@example.com ", "amount": 0 } | 400 Invalid amount | Pass
TC-AUTH-005 | POST /transaction/initialize | Initialize Transaction | Validate that the API returns an appropriate error when the email format is invalid. | • Merchant is active • Request body is valid except for incorrect email format | 1. Send POST request to /transaction/initialize. 2. Provide an invalid email format (e.g., "testemail.com"). 3. Submit the request. 4. Validate the error response. | Request Body: { "email": "invalid-email", "amount": 5000 } | 400 Invalid email | Pass
TC-AUTH-006 | POST /transaction/initialize | Initialize Transaction | Validate that the API rejects requests when a Live Secret Key is used in Test Mode. | • Environment is Test Mode (sandbox) • Developer mistakenly sets a Live Secret Key (sk_live_xxxx) | 1. Set Authorization header to Bearer sk_live_xxxxx. 2. Send POST request to /transaction/initialize. 3. Submit valid transaction request. 4. Observe the authentication failure. | Header: Authorization: Bearer sk_live_xxxxxx | 401 Invalid Key | Pass
TC-AUTH-007 | POST /transaction/initialize | Initialize Transaction | Validate that the API returns a 405 error when a method other than POST is used. | • API route exists and only accepts POST | 1. Send a GET, PUT, or DELETE request to /transaction/initialize. 2. Observe server response. | Example: Method: GET URL: /transaction/initialize | 405 Method Not Allowed | Fail
TC-AUTH-008 | POST /transaction/initialize | Initialize Transaction | Unsuccessful initialization with valid amount + email due to insufficient funds | User is registered and logged in. Account has insufficient balance. | 1. Send POST request to /transaction/initialize with insufficient balance 2. Include required fields: email, amount, currency, metadata 3. Observe API response 4. Validate returned status, reference, and authorization URL 5. Verify response mapping to ISO 8583 code (if failure) | Card: 4000000000001000 – INSUFFICIENT_FUNDS | Paystack API returns status: false. Error message: "Insufficient funds" | Pass
TC-AUTH-009 | POST /transaction/initialize | Initialize Transaction | Unsuccessful initialization with valid amount + email, using a stolen/lost card | User is registered and logged in. Card has been reported lost or stolen. | 1. Send POST request to /transaction/initialize with lost/stolen card 2. Include required fields: email, amount, currency, metadata 3. Observe API response 4. Validate returned status, reference, and authorization URL 5. Verify response mapping to ISO 8583 code (if failure) | 5114610000004770 – CARD_LOST_OR_STOLEN | Transaction declined. Message: "Card reported lost or stolen" | Pass
TC-AUTH-010 | POST /transaction/initialize | Initialize Transaction | Unsuccessful initialization with valid amount + email, using an expired card | User is registered and logged in. Card is expired. | 1. Send POST request to /transaction/initialize with an expired card 2. Include required fields: email, amount, currency, metadata 3. Observe API response 4. Validate returned status, reference, and authorization URL 5. Verify response mapping to ISO 8583 code (if failure) | Card: 4242420000000090 – EXPIRED_CARD | Decline. Message: "Expired card" | Pass
TC-AUTH-011 | POST /transaction/initialize | Initialize Transaction | Unsuccessful initialization with valid amount + email due to limit exceeded | User is registered and logged in. Spending limit on card is exceeded. | 1. Send POST request to /transaction/initialize with a card that has limit 2. Include required fields: email, amount, currency, metadata 3. Observe API response 4. Validate returned status, reference, and authorization URL 5. Verify response mapping to ISO 8583 code (if failure) | Card: 4009830000001980 – LIMIT_EXCEEDED | Decline. Message: "Spending limit exceeded" | Pass
TC-AUTH-012 | POST /transaction/initialize | Initialize Transaction | Unsuccessful initialization with valid amount + email due to failure in payment processing | User is registered and logged in. Payment gateway encounters a processing error. | 1. Send POST request to /transaction/initialize 2. Include required fields: email, amount, currency, metadata 3. Observe API response 4. Validate returned status, reference, and authorization URL 5. Verify response mapping to ISO 8583 code (if failure) | Card: 4347699988887770 – GENERAL_PAYMENT_PROCESSING_ERROR | Decline. Message: "Processing error" | Pass
TC-AUTH-013 | POST /transaction/initialize | Initialize Transaction | Unsuccessful initialization with valid amount + email due to high risk (fraud detection) | User is registered and logged in. Transaction flagged as high risk by fraud detection system. | 1. Send POST request to /transaction/initialize with 2. Include required fields: email, amount, currency, metadata 3. Observe API response 4. Validate returned status, reference, and authorization URL 5. Verify response mapping to ISO 8583 code (if failure) | Card: 5121220000006920 – HIGH_RISK_ERROR | Transaction declined. Message: "High risk transaction"
TC-AUTH-014 | POST /transaction/initialize | Initialize Transaction | Validate that a transaction initializes successfully but payment fails due to insufficient funds during card processing. | • Merchant account active • Valid amount, email, callback URL • Test card configured to simulate insufficient funds | 1. Send POST request to /transaction/initialize with valid amount, email, and callback URL. 2. Redirect to authorization/payment page using the returned authorization_url. 3. Enter card details configured to simulate insufficient funds. 4. Attempt to complete the payment. 5. Confirm that payment fails and reference is generated. 6. Optional: Call GET /transaction/verify/{reference} to verify status. | Request Body: { "email": "user@example.com ", "amount": 10000, "callback_url": "https://merchant.com/callback " } Test Card: Insufficient funds card (e.g., Paystack test card that returns insufficient_funds) |  | Descope
TC-AUTH-015 | GET /transaction/verify/{reference} | Verify Transaction | Validate that the API returns correct transaction details for a successful payment. | • Transaction must have been initialized AND paid successfully • Reference is available | 1. Successfully initialize and complete a payment. 2. Copy the transaction reference. 3. Send GET request to /transaction/verify/{reference}. 4. Validate returned fields: amount, currency, customer email, channel, fees, timestamps. | GET /transaction/verify/{reference} Example Reference: PSK_ref_123456789 | Status = success
TC-AUTH-016 | GET /transaction/verify/{reference} | Verify Transaction | Validate that the API correctly returns a failed transaction status after a payment attempt fails. | • A payment attempt must have been made • Payment failed (insufficient funds, incorrect PIN, card declined, etc.) • Reference is available | 1. Initialize a transaction. 2. Attempt payment using a card that triggers a decline. 3. Obtain transaction reference from callback or from the initialize response flow. 4. Send GET request to /transaction/verify/{reference}. 5. Validate "status": "failed" and "gateway_response". | GET /transaction/verify/{reference} Example Failure Reasons: • "insufficient_funds" • "declined" • "incorrect_pin" | Status = failed | Pass
TC-AUTH-017 | GET /transaction/verify/{reference} | Verify Transaction | Validate API behavior when verifying a transaction using a reference that does not exist in the system. | • Use a completely fake or random reference not associated with any transaction. | 1. Send GET request to /transaction/verify/{reference} using an invalid reference string (e.g., abc123xyz_invalid). 2. Observe response. | GET /transaction/verify/invalid_ref_123 | 404 Not Found | Pass
TC-AUTH-018 | GET /transaction/verify/{reference} | Verify Transaction | Validate that the API returns an error when no reference is supplied. | No reference | 1. Send GET request to /transaction/verify/ without specifying a reference. 2. Observe the response. | GET /transaction/verify/ | 400 Bad Request | Pass
TC-AUTH-019 | GET /transaction/verify/{reference} | Verify Transaction | Validate that the API+D21 returns the correct status for a transaction reference that has expired due to timeout or customer abandonment. | • Initialize a transaction. • Do not complete payment. • Allow the session to expire (Paystack marks as abandoned). | 1. Initialize a transaction to generate a reference. 2. Do not proceed with payment until expiration. 3. Send GET request to /transaction/verify/{reference}. 4. Observe status. | GET /transaction/verify/{expired_reference} | Status = abandoned | Pass
TC-AUTH-020 | GET /transaction/verify/{reference} | Verify Transaction | Validate that the API denies access when the request is made with an invalid or missing secret key. | • Use an invalid, expired, or no secret key. | 1. Set Authorization: Bearer invalid_key_1234 2. Send GET request to /transaction/verify/{reference}. 3. Observe response. | Invalid headers: Authorization: Bearer abc123_invalid_key | 401
TC-AUTH-021 | GET /transaction/verify/{reference} | Verify Transaction | Validate verification results for a transaction where initialization was successful but payment failed due to insufficient funds. | • Transaction initialized with valid amount + email • Payment attempted with insufficient funds test card | 1. Send POST /transaction/initialize with valid fields. 2. Proceed to the payment authorization page. 3. Enter test card that triggers insufficient funds. 4. Attempt the payment → failure. 5. Take the returned reference. 6. Call GET /transaction/verify/{reference}. | Test Card: Insufficient funds card Amount: e.g., 10,000 Email: user@example.com |  | WIP
TC-AUTH-022 | GET /transaction | Fetch all transactions | Fetch all transactions with valid API key | Multiple transactions exist | 1. Send GET /transaction 2. Observe response. | Sandbox API key | 200 OK, returns array
TC-AUTH-023 | GET /transaction | Fetch all transactions | Fetch filtered transactions (date range) | At least one transaction exists | 1. Send GET /transaction 2. Observe response. |  | Filter applied correctly | Fail
TC-AUTH-024 | GET /transaction | Fetch all transactions | Validate API behavior when fetching transactions without providing an authorization key. | • No API key or empty Authorization header | 1. Send GET /transaction without Authorization header. 2. Observe response. | No auth header | 401 Unauthorized | Pass
TC-AUTH-025 | GET /transaction | Fetch all transactions | Validate system behavior when user provides unsupported or incorrect date formats. | Valid API key | 1. Send GET request to /transaction?from=2024/13/99&to=12-10-2024 (invalid). 2. Observe validation error. | from=2024/13/99 to=12/10/24 | 400 Bad Request | Fail
TC-AUTH-026 | GET /transaction | Fetch all transactions | Validate API behavior when the endpoint is accessed with POST instead of GET. | Valid API key | 1. Send POST request to /transaction. 2. Observe response. | POST /transaction | 404 Not Found | Pass
TC-AUTH-027 | GET /transaction | Fetch all transactions | Validate successful retrieval of all transactions with valid credentials and optional filters. | • Valid API key • Existing transactions | 1. Send GET request to /transaction with valid Authorization header. 2. Apply optional filters if needed (date, status). 3. Observe returned transaction list. | GET /transaction |  | Descope
TC-AUTH-028 | GET /transaction/export | Export Transactions | Validate successful export of transactions into downloadable file format. | • Valid API key • Transactions exist | 1. Send GET /transaction/export. 2. Wait for file generation. 3. Confirm link or file download. | GET /transaction/export | File download link generated | Fail
TC-AUTH-029 | GET /transaction/export | Export Transactions | Validate behavior when attempting export without authorization key. | No key | 1. Send GET /transaction/export without Authorization header. 2. Observe response. | No API key | 401 | Pass
TC-AUTH-030 | GET /transaction/export | Export Transactions | Validate behavior when query range contains zero transactions. | • Valid API key • Empty dataset for selected dates | 1. Send GET /transaction/export?from=2024-01-01&to=2024-01-02 where no transactions exist. 2. Observe response. | from=2024-01-01 to=2024-01-02 | Empty file | Descope
TC-AUTH-031 | GET /transaction/export | Export Transactions | Validate error handling for incorrect date filter formats. | Valid API key | 1. Send GET /transaction/export?from=2025/99/99&to=10-2024 (invalid). 2. Observe server validation. | Invalid date formats | 400 | Descope

## DISPUTE API
Test Case ID | API / Feature | Title | Description | Pre-conditions | Steps | Test Data | Expected Result | Status
TC-DISP-001 | GET /dispute | List Disputes | List disputes filed | User is authenticated with valid API key | Send GET request to /dispute | None | Successfully fetches all disputes. Status 200. Response contains dispute list | Pass
TC-DISP-002 | GET /dispute | List Disputes | List disputes filed | No authentication token provided | Send GET request to /dispute without auth header | None | Request fails. Status 401 Unauthorized. Error message: "Missing authentication" | Fail
TC-DISP-003 | GET /dispute | List Disputes | List disputes filed | User is authenticated | Send POST request to /dispute instead of GET | None | Request fails. Status 405 Method Not Allowed | Pass
TC-DISP-004 | GET /dispute/{id} | Fetch Dispute | Get more details about a dispute | User is authenticated, dispute exists | Send GET request to /dispute/{id} with valid dispute ID | Valid dispute ID | Successfully fetches dispute details. Status 200. Response contains dispute info | Pass
TC-DISP-005 | GET /dispute/{id} | Fetch Dispute | Get more details about a dispute | User is authenticated | Send GET request to /dispute/{id} with invalid/nonexistent ID | Invalid dispute ID | Request fails. Status 404 Not Found. Error message: "Dispute not found" | Pass
TC-DISP-006 | GET /dispute/{id} | Fetch Dispute | Get more details about a dispute | User is authenticated | Send GET request to /dispute/{id} with alphanumeric ID | Alphanumeric string as ID | Request fails. Status 400 Bad Request. Error message: "Invalid dispute ID" | Pass
TC-DISP-007 | Add Evidence | Successful Evidence Creation | Validate that evidence can be added with all required fields | Valid dispute ID exists | 1. Send POST request with valid headers and body | customer_email, customer_name, customer_phone, service_details | 200 OK, “Evidence created”, evidence saved | Pass
TC-DISP-008 | Add Evidence | Evidence Creation With Optional Fields | Verify evidence creation with optional fields delivery_address and delivery_date | Valid dispute ID | 1. Send POST with all fields including optional ones | Same as above + delivery_address + delivery_date | 200 OK, optional fields saved | Pass
TC-DISP-009 | Add Evidence | Missing Required Email | Validate API error when customer_email is missing | Valid dispute ID | 1. Send POST without customer_email | customer_email: null | 400 Bad Request, email required | Pass
TC-DISP-010 | Add Evidence | Invalid Email Format | Validate email format validation | Valid dispute ID | 1. Send POST with invalid email | customer_email: "invalid" | 400 Bad Request | Pass
TC-DISP-011 | Add Evidence | Missing Customer Name | Validate error for missing name | Valid dispute ID | 1. Send POST without customer_name | customer_name: "" | 400 Bad Request | Descope
TC-DISP-012 | Add Evidence | Missing Phone Number | Validate error for missing phone | Valid dispute ID | 1. Send POST without customer_phone | customer_phone: "" | 400 Bad Request | Descope
TC-DISP-013 | Add Evidence | Missing Service Details | Validate error for missing service_details | Valid dispute ID | 1. Send POST without service_details | service_details: null | 400 Bad Request | Descope
TC-DISP-014 | Add Evidence | Invalid Delivery Date Format | Validate ISO 8601 validation | Valid dispute ID | 1. Send POST with wrong date format | delivery_date: "12/01/25" | 400 Bad Request | Descope
TC-DISP-015 | Add Evidence | Invalid Dispute ID | Check behavior on invalid dispute ID | Invalid dispute ID | 1. Send POST to /dispute/999999/evidence | dispute_id: 999999 | 404 Not Found | Pass
TC-DISP-016 | Add Evidence | Unauthorized Access | Validate no Auth header | None | 1. Send POST without Authorization header | No Auth Token | 401 Unauthorized | Pass
TC-DISP-017 | Add Evidence | Invalid Token | Validate token error | Invalid token available | 1. Send POST with wrong token | Authorization: Bearer WRONG_KEY | 401 Unauthorized | Pass
TC-DISP-018 | Get Upload URL | Successful Upload URL Generation | Validate URL generation with valid data | Valid dispute ID | 1. Send GET with valid filename query | upload_filename=receipt.pdf | 200 OK, signedUrl + fileName returned | Pass
TC-DISP-019 | Get Upload URL | Missing Filename | Validate error when upload_filename is empty | Valid dispute ID | 1. Send GET without upload_filename | upload_filename= | 400 Bad Request | Pass
TC-DISP-020 | Get Upload URL | Invalid Filename | Validate filename must contain extension | Valid dispute ID | 1. Send GET with invalid filename | upload_filename="nofile" | 400 Bad Request | Pass
TC-DISP-021 | Get Upload URL | Invalid Dispute ID | Validate behavior for invalid dispute ID | Invalid dispute ID | 1. Send GET to invalid dispute ID | dispute_id: 999 | 404 Not Found | Pass
TC-DISP-022 | Get Upload URL | Unauthorized Access | Validate missing auth header behavior | None | 1. Send GET without Authorization header | None | 401 Unauthorized | Pass
TC-DISP-023 | Get Upload URL | Invalid Token | Validate wrong token behavior | Invalid token available | 1. Send GET using wrong token | Bearer WRONG_KEY | 401 Unauthorized | Pass
TC-DISP-024 | Get Upload URL | Filename With Special Characters | Validate validation for special characters | Valid dispute ID | 1. Send GET with filename "$%^.pdf" | upload_filename="$%^.pdf" | 400 Bad Request | Pass
TC-DISP-025 | Resolve Dispute | Successful Resolution – Merchant Accepted | Validate successful resolution flow | Valid dispute ID, evidence uploaded | 1. Send POST with valid payload | resolution: merchant-acceptedmessage: OKrefund_amount: 0 | 200 OK, dispute updated | Pass
TC-DISP-026 | Resolve Dispute | Successful Resolution – Declined | Validate decline flow | Valid dispute ID | 1. Send POST with decline payload | resolution: declinedmessage: Reason here | 200 OK | Pass
TC-DISP-027 | Resolve Dispute | Missing Resolution | Ensure error for missing required field | Valid dispute ID | 1. Send POST without resolution | resolution: null | 400 Bad Request | Pass
TC-DISP-028 | Resolve Dispute | Invalid Resolution Value | Validate strict values accepted | Valid dispute ID | 1. Send POST with invalid value | resolution="approve" | 400 Bad Request | Pass
TC-DISP-029 | Resolve Dispute | Missing Message | Validate message required | Valid dispute ID | 1. Send POST without message | message: "" | 400 Bad Request | Pass
TC-DISP-030 | Resolve Dispute | Missing Refund Amount | Validate refund amount required | Valid dispute ID | 1. Send POST without refund amount | refund_amount: null | 400 Bad Request | Pass
TC-DISP-031 | Resolve Dispute | Invalid Refund Amount Format | Validate type checking | Valid dispute ID | 1. Send POST with non-integer value | refund_amount: "1000" | 400 Bad Request | Pass
TC-DISP-032 | Resolve Dispute | Invalid uploaded_filename | Validate error when filename incorrect | Valid dispute ID | 1. Use wrong uploaded_filename | filename: wrong.pdf | 400 Bad Request | Pass
TC-DISP-033 | Resolve Dispute | Link Evidence ID | Validate evidence linking for fraud | Valid dispute ID + evidence | 1. Send POST with evidence | evidence: 21 | 200 OK | Pass
TC-DISP-034 | Resolve Dispute | Invalid Dispute ID | Validate error for non-existent dispute | Invalid dispute ID | 1. Send POST to invalid ID | dispute_id: 999999 | 404 Not Found | Pass
TC-DISP-035 | Resolve Dispute | Unauthorized Request | Validate no-auth behavior | None | 1. Send POST without Authorization | no token | 401 Unauthorized | Pass
TC-DISP-036 | Resolve Dispute | Invalid Token | Validate wrong token handling | Invalid token available | 1. Send POST with wrong token | Bearer WRONG_KEY | 401 Unauthorized | Pass

## REFUND API
Test Case ID | API / Feature | Title | Description | Pre-conditions | Steps | Test Data | Expected Result | Status
TC-REF-001 | POST /refund | Create Refund | Initiate a refund | A successful transaction exists | POST /refund with valid transaction reference and full amount | Card: 5425233430109903 – Success (00) | Full refund initiated. Status: "success" | Pass
TC-REF-002 | POST /refund | Create Refund | Initiate a refund | A successful transaction exists | POST /refund with valid transaction reference and partial amount | Card: 5425233430109903 – Success (00) | Partial refund initiated. Status: "success" | Pass
TC-REF-003 | POST /refund | Create Refund | Initiate a refund | A successful transaction exists | POST /refund with invalid transaction reference | Card: 5425233430109903 – Success (00) | Request fails. Status: "error". Message: "Invalid transaction reference" | Pass
TC-REF-004 | POST /refund | Create Refund | Initiate a refund | A successful transaction exists | POST /refund with amount greater than transaction | Card: 5425233430109903 – Success (00) | Request fails. Status: "error". Message: "Refund amount exceeds transaction amount" | Pass
TC-REF-005 | POST /refund | Create Refund | Initiate a refund | A successful transaction exists | POST /refund on an already refunded transaction | Card: 4000160000004140 – REFUND_FAILED | Request fails. Status: false. Message: "Refund failed" | Pass
TC-REF-006 | POST /refund | Create Refund | Initiate a refund | A successful transaction exists | POST /refund with transaction reference but missing amount | Card: 5425233430109903 – Success (00) | Request fails. Status: "error". Message: "Amount is required" | Fail
TC-REF-007 | POST /refund | Create Refund | Initiate a refund | A successful transaction exists | POST /refund with invalid/wrong API key | Card: 5425233430109903 – Success (00) | Request fails. Status: 401 Unauthorized. Message: "Invalid API key" | Pass
TC-REF-008 | POST /refund/{id}/retry | Retry Refund | Retry a refund with a needs-attention status by providing bank account details | A successful transaction exists, previous refund attempt status is "needs-attention" | POST /refund → POST /refund/{id}/retry with bank account details | Card: 5425233430109903 – Success (00) | Retry succeeds. Status: "success". Refund processed | Pass
TC-REF-009 | POST /refund/{id}/retry | Retry Refund | Retry a refund with a needs-attention status | A successful transaction exists, previous refund attempt not retryable | POST /refund/{id}/retry | Card: 5425233430109903 – Success (00) | Request fails. Status: "error". Message: "Refund not retryable" | Pass
TC-REF-010 | POST /refund/{id}/retry | Retry Refund | Retry a refund with a needs-attention status | A successful transaction exists | POST /refund/{id}/retry with wrong refund ID | Card: 5425233430109903 – Success (00) | Request fails. Status: 404 Not Found. Message: "Refund ID not found" | Pass
TC-REF-011 | GET /refund | List Refunds | List refunds available | A successful transaction exists | GET /refund | Card: 5425233430109903 – Success (00) | List of refund attempts returned. Status 200. Refund status visible | Pass

## VERIFICATION API
Test Case ID | API / Feature | Title | Description | Pre-conditions | Steps | Test Data | Expected Result | Status
TC-VER-001 | GET /bank/resolve | Resolve Account | Confirm an account belongs to the right customer | User is authenticated; valid account exists | Send GET /bank/resolve?account_number=<valid>&bank_code=<valid> | Valid account number + valid bank code | Successfully resolves account. Status 200. Response confirms account ownership | Pass
TC-VER-002 | GET /bank/resolve | Resolve Account | Confirm an account belongs to the right customer | User is authenticated | Send GET /bank/resolve?account_number=<invalid>&bank_code=<valid> | Invalid account number + valid bank code | Request fails. Status 404 Not Found. Message: "Account not found" | Pass
TC-VER-003 | GET /bank/resolve | Resolve Account | Confirm an account belongs to the right customer | User is authenticated | Send GET /bank/resolve?account_number=<valid>&bank_code=<invalid> | Valid account number + invalid bank code | Request fails. Status 400 Bad Request. Message: "Invalid bank code" | Pass
TC-VER-004 | GET /bank/resolve | Resolve Account | Confirm an account belongs to the right customer | User is authenticated | Send GET /bank/resolve with empty account_number or bank_code | Empty account_number/bank_code | Request fails. Status 400 Bad Request. Message: "Required fields missing" | Pass
TC-VER-005 | GET /decision/bin/{bin} | Resolve BIN | Get more information about a customer's card | User is authenticated; BIN exists | Send GET /decision/bin/{bin} | Valid BIN (first 6 digits of a card) | Successfully returns card information. Status 200. Response includes card brand, type, and bank | Pass
TC-VER-006 | GET /decision/bin/{bin} | Resolve BIN | Get more information about a customer's card | User is authenticated | Send GET /decision/bin/{bin} where BIN < 6 digits | BIN with fewer than 6 digits | Request fails. Status 400 Bad Request. Message: "Invalid BIN length" | Pass
TC-VER-007 | GET /decision/bin/{bin} | Resolve BIN | Get more information about a customer's card | User is authenticated | Send GET /decision/bin/{bin} where BIN contains non-numeric characters | Non-numeric BIN | Request fails. Status 400 Bad Request. Message: "BIN must be numeric" | Pass
TC-VER-008 | POST /bank/validate | Successful Account Validation | Verify that the system correctly validates a valid bank account and returns account details. | Valid bank code and active account number exist in the system. | 1. Send a POST request to /bank/validate with all required fields.2. Provide valid bank code and valid account number.3. Observe API response. | json<br>{<br> "bank_code": "632005",<br> "country_code": "ZA",<br> "account_number": "0123456789",<br> "account_name": "Ann Bron",<br> "account_type": "personal",<br> "document_type": "identityNumber",<br> "document_number": "1234567890123"<br>} | API returns:• 200 OK• status: true• Correct account name and bank details returned• Message: “Account validated successfully” | Pass
TC-VER-009 | POST /bank/validate | Invalid Bank Code | Ensure the system rejects invalid or unsupported bank codes. | System must have a list of valid bank codes. | 1. Send POST request with invalid bank code.2. Observe the response. | json<br>{<br> "bank_code": "999999",<br> "country_code": "ZA",<br> "account_number": "0123456789"<br>} | API returns:• 400 Bad Request• status: false• Message: "Invalid bank code"• No account details returned | Pass
TC-VER-010 | POST /bank/validate | Invalid or Non-existent Account Number | Check system behavior when an account number does not exist at the given bank. | Valid bank code available. | 1. Send POST request with valid bank code but invalid account number.2. Observe response. | json<br>{<br> "bank_code": "632005",<br> "account_number": "0000000000"<br>} | API returns:• 404 Not Found• status: false• Message: “Account not found” | Pass
TC-VER-011 | POST /bank/validate | Missing Required Fields | System should appropriately reject requests missing mandatory fields. | None | 1. Send POST request without account number or bank code.2. Observe API behavior. | json<br>{<br> "bank_code": "632005"<br>} | API returns:• 400 Bad Request• status: false• Message: “Missing required fields” or “Account number is required” | Pass

## CUSTOMER API
Test Case ID | API / Feature | Title | Description | Pre-conditions | Steps | Test Data | Expected Result | Status
TC-CUS-001 | POST /customer | Create Customer | Create a customer with first_name, last_name, and phone | User is authenticated | POST /customer with valid customer data | { "first_name": "John", "last_name": "Doe", "email": "john.doe@example.com", "phone": "+27123456789" } | Customer created successfully. Status 201. Response includes customer ID and details | Pass
TC-CUS-002 | POST /customer | Create Customer | Create a customer with a duplicate email address | User is authenticated; email already exists | POST /customer with duplicate email | { "first_name": "Jane", "last_name": "Doe", "email": "john.doe@example.com", "phone": "+27123456789" } | Request fails. Status 409 Conflict. Message: "Email already exists" | Fail
TC-CUS-003 | POST /customer | Create Customer | Create a customer with an invalid email address | User is authenticated | POST /customer with invalid email format | { "first_name": "Mark", "last_name": "Smith", "email": "mark.smith@invalid", "phone": "+27123456789" } | Request fails. Status 400 Bad Request. Message: "Invalid email format" | Pass
TC-CUS-004 | POST /customer | Create Customer | Create a customer without first_name, last_name, and phone | User is authenticated | POST /customer with missing required fields | { "email": "new.user@example.com" } | Request fails. Status 400 Bad Request. Message: "Missing required fields" | Pass
TC-CUS-005 | PUT /customer/{id} | Update Customer | Update name or phone | User is authenticated; customer exists | PUT /customer/{id} with updated name or phone | { "first_name": "John", "last_name": "Smith", "phone": "+27123456780" } | Customer updated successfully. Status 200. Response includes updated details | Pass
TC-CUS-006 | PUT /customer/{id} | Update Customer | Invalid customer ID | User is authenticated | PUT /customer/{id} with non-existent customer ID | { "first_name": "John", "last_name": "Smith", "phone": "+27123456780" } | Request fails. Status 404 Not Found. Message: "Customer not found" | Pass
TC-CUS-007 | PUT /customer/{id} | Update Customer | Empty body | User is authenticated; customer exists | PUT /customer/{id} with empty body {} | None | Request fails. Status 400 Bad Request. Message: "Request body cannot be empty" | Pass

## DVA API
Test Case ID | API / Feature | Title | Description | Pre-conditions | Steps | Test Data | Expected Result | Status
TC-DVA-001 | POST /dedicated_account | Create DVA | Create a valid Dedicated Virtual Account | User is authenticated; customer exists | POST /dedicated_account with valid customer ID and bank code | { "customer_id": "12345", "bank_code": "001" } | DVA created successfully. Status 200 OK. Response contains DVA details | Pass
TC-DVA-002 | POST /dedicated_account | Create DVA | Unsupported bank | User is authenticated; customer exists | POST /dedicated_account with unsupported bank code | { "customer_id": "12345", "bank_code": "999" } | Request fails. Status 400 Bad Request. Message: "Unsupported bank" | Pass
TC-DVA-003 | POST /dedicated_account | Create DVA | Missing customer | User is authenticated | POST /dedicated_account without customer ID | { "bank_code": "001" } | Request fails. Status 400 Bad Request. Message: "Missing customer information" | Pass
TC-DVA-004 | POST /dedicated_account/assign | Assign DVA | Successful assignment | User is authenticated; DVA exists; customer exists | POST /dedicated_account/assign with valid DVA ID and customer ID | { "dva_id": "DVA12345", "customer_id": "12345" } | DVA assigned successfully. Status 200 OK. Response confirms assignment | Pass
TC-DVA-005 | POST /dedicated_account/assign | Assign DVA | DVA already assigned | User is authenticated; DVA already assigned | POST /dedicated_account/assign with DVA ID already assigned | { "dva_id": "DVA12345", "customer_id": "12345" } | Request fails. Status 409 Conflict. Message: "DVA already assigned" | Pass
TC-DVA-006 | POST /dedicated_account/assign | Assign DVA | Invalid DVA ID | User is authenticated; customer exists | POST /dedicated_account/assign with non-existent DVA ID | { "dva_id": "INVALID123", "customer_id": "12345" } | Request fails. Status 404 Not Found. Message: "DVA not found" | Pass
TC-DVA-007 | GET /dedicated_account | List all DVAs | Verify that the system returns all available Dedicated Virtual Accounts | At least one DVA exists in the system | 1. Send GET request to /dedicated_account2. Observe response | None | Response status is truemessage is "List of Dedicated Virtual Accounts"data array contains all DVAs | Pass
TC-DVA-008 | GET /dedicated_account | No DVAs available | Verify the system behavior when no DVAs exist | No DVA exists in the system | 1. Send GET request to /dedicated_account2. Observe response | None | Response status is truemessage is "List of Dedicated Virtual Accounts"data array is empty [] | Fail
TC-DVA-009 | GET /dedicated_account | Invalid Authorization | Verify response when authorization header is missing or invalid | Authorization header not provided or incorrect | 1. Send GET request to /dedicated_account without authorization header2. Observe response | None | Response status is falsemessage indicates unauthorized access or missing auth | Pass